## 2024 Timeline
CRHC HUD CoC Program MI-508 Competition Calendar
2024/2025 NOFO Schedule (PY 2025/2026 & 2026/2027) | Date | Time | Location / Notes
2024/2025 NOFO Announced and Released by HUD | 2024-07-31 | N/A | Circulated to CoC network on August 8, 2024.
Finance Committee review of PY2025/26 application and scoring/ranking process and discussed project reallocations | September 6-12, 2024 | TBD | Virtual Meetings
Local competition notice out to public and stakeholders - includes notice to network and reminder about deadlines/intent to apply | 2024-09-13 | 17:00 | Post to CRHC website, City website, City Post, LSJ, the Chronicle, Salus Center
HUD Community Application Q & A during NOFO Collaborative Meetings | September 10th, and 17th and October 1st, 8th, 15th, and 22nd | 9am - 11am | TEAMS Link: https://teams.microsoft.com/l/meetup-join/19%3ameeting_NTVjZDc5YzktNGFiZC00ZDMxLWI2NTEtMWE0OTBkNjIzZDZl%40thread.v2/0?context=%7b%22Tid%22%3a%22344fa115-1c4f-45f1-b62b-44e4773f6c56%22%2c%22Oid%22%3a%229f512084-cb4a-4364-af8e-8671ace48307%22%7d
2024/2025 CoC Program NOFO Collaborative Meeting (PY 2025-2026) | Tuesday, September 10, 2024 | 9am-11am | Virtual Meeting: See above or link in Calendar of Events on CRHC Website
2024/2025 CoC Program NOFO Collaborative Meeting (PY 2025-2026) | 2024-09-17 | 9am-11am | Virtual Meeting: See above or link in Calendar of Events on CRHC Website
Notice of Intent to Apply due to CRHC (CoC) | 2024-09-20 | 12 noon | email to: glhrncoordinator@gmail.com
CoC Board Meeting- adjusted decision-making based on intents to apply? | 2024-09-24 | 9am-11am | Virtual Meeting: See above or link in Calendar of Events on CRHC Website
Grantee Applications due to CoC Coordinator via Email | 2024-09-30 | noon | All project applications must be submitted to the CoC no later than 30-days before HUD's CoC Program Application Submission deadline. Email applications to CoC Coordinator at glhrncoordinator@gmail.com
2024/2025 CoC Program NOFO Collaborative Meeting (PY 2025-2026) | 2024-10-01 | 9am-11am | Virtual Meeting: See above or link in Calendar of Events on CRHC Website
Ranking/Scoring Committee Selected and Trained- Reviewed Scoring Rubric | Between Sept 27th and Oct 2nd | TBD | Look for email from Finance Committee Chair
Apps sent out to be reviewed & scored (Rankers/Reviewers needed) | 2024-10-02 | 12 noon | see Application Announcement
2024/2025 CoC Program NOFO Collaborative Meeting (PY 2025-2026) | 2024-10-08 | 9am-11am | Virtual Meeting: See above or link in Calendar of Events on CRHC Website
Score sheets due to Collaborative Applicant/HMIS Administrator/CoC Manager | Monday, October 7, 2024 | 12 noon | email to: glhrncoordinator@gmail.com
New CA and HMIS Lead are established in ESNAPS | 2022-09-09 |  | Remove? they're not new this year.
CoC Project Application ranking meeting (Finance Committee) | Thursday, October 10, 2024 | 9-11am | In person or by zoom. Recommendations sent to CoC board same day.
Board approval of ranking and funding recommendations | Friday, October 11, 2024 | 17:00 | Electronic or following Ranking/Reallocation meeting, if quorum.
Public Notification of Ranked Project Applications | Monday, October 14, 2025 | 17:00 | Per NOFO, must be sent 15-days Prior to HUD application submission deadline. See Pg 75
Written notifications of application ranking and applications that are approved, reduced, or rejected, sent by CA | Monday, October 14, 2025 | 17:00 | Per NOFO, posted 15-days Prior to HUD application submission deadline. Pg 75
2024/2025 CoC Program NOFO Collaborative Meeting (PY 2025-2026) | 2024-10-15 | 9am-11am | Virtual Meeting: See above or link in Calendar of Events on CRHC Website
2024/2025 CoC Program NOFO Collaborative Meeting (PY 2025-2026) | 2024-10-22 | 9am-11am | Virtual Meeting: See above or link in Calendar of Events on CRHC Website
HUD Collaborative Application FINAL Draft to CoC Board (and Stakeholders) | 2024-10-22 | 17:00 | Via CRHC email
Accepted applications due in esnaps | 2024-10-24 | 10pm | https://esnaps.hud.gov
Deadline for Board feedback on CRHC Collaborative Application | Friday, October 25, 2024 | 5pm | email to: glhrncoordinator@gmail.com
CRHC Board approval of Collaborative Application | 2024-10-28 | by noon | Electronic Vote: Look for email
Collaborative Application posted to website for public review | 2024-10-28 | 17:00 | See CRHC Website
CRHC internal due date for submission | Monday, October 28, 2024 | 17:00 | Everything together to approve and hit submit after board meeting on 10/29
Collaborative App, Project Apps & Priority List submitted to HUD | Wednesday, October 30, 2024 | 8pm | Per NOFO due by 8pm. Internal goal due by 5pm on Esnap
HUD required deadlines and need special attention

## Sheet1 (hidden)
2021 NOFO Schedule | Date | Time | Location / Notes
2021 NOFO Released by HUD | 2019-07-03
Local competition notice | 2019-08-01
Notice of Intent to Apply | 2019-08-12 | noon | email to: coordinator@glhrn.org
CoC NOFO Application Meeting | 2019-08-15 | 11AM | Zoom
Applications sent to agencies with intent to apply | 2019-08-15 | End of Day
New applicant Q&A session (optional) | 2019-08-21 | 2PM | HRCS conference room - 4th floor city hall
Applications due to HRCS | 2019-08-22 | noon | email to: matt.stevenson@lansingmi.gov
Apps sent out to be reviewed & scored (Rankers/Reviewers needed) | 2019-08-22 | End of Day | see Application Announcement
Score sheets due to HRCS | 2019-08-26 | noon | email to: matt.stevenson@lansingmi.gov
CoC Application Ranking Meeting | 2019-08-27 | Following Board Mtg (approx. 11AM) | Zoom
Board Approval of Recommendations | 2019-08-27 |  | Electronic or following Ranking meeting
Written Notifications of Application Ranking sent by HRCS | 2019-08-28
Optional Meeting for accepted applications (RSVP to HRCS) | 2019-08-29 | noon | Zoom
Accepted apps due in esnaps | 2019-09-10 | End of Day
HUD Collaborative Application Draft to CoC Board - target | 2019-09-23 | noon
HUD Collaborative App posted to website for public review | 2019-09-23 | noon
Deadline for feedback on Collab App | 2019-09-24 | End of Day | email to: katrina.urista@lansingmi.gov
Collaborative App, Project Apps & Priority List to HUD | 2019-09-25 | End of Day